## Instructions
RadioLife.app — UAT & Test Cases
Environments
• PRODUCTION (live): https://radiolife.app — test the real, deployed app here.
• PREVIEW (dev): the Emergent preview URL — where new changes land before deploy.
Always record which environment a defect was found on.
Test accounts
• Admin: admin@bigfm.dubai / AdminPass123!
• Merchant: test@bigfm.dubai / TestUser123!
• User: demo@bigfm.dubai / DemoPass123!
How to use this workbook
1. Go to the 'UAT Test Cases' tab.
2. Each row is one test. Follow 'Test Steps' with the given 'Test Data'.
3. Compare what you see to 'Expected Result'.
4. Fill 'Actual Result', set 'Status' (Pass / Fail / Blocked / N/A) from the dropdown,
add your name in 'Tester', the 'Date', and any 'Notes / Defect ID'.
5. The 'Summary' tab auto-counts Pass/Fail/Blocked as you fill Status.
Priority key
• P0 = critical (must pass to ship) • P1 = high • P2 = medium/nice-to-have
Platform: Web = radiolife.app / preview web · Mobile = Expo app · Both = verify on each.
Tip: use Data > Filter on the test-cases tab to run by Module, Priority, or Platform.

## UAT Test Cases
TC ID | Module | Feature | Priority | Platform | Type | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Tester | Date | Notes / Defect ID
A-01 | Authentication | Login | P0 | Both | Functional | Registered user; on Login screen | 1. Enter email & password 2. Tap/Click Sign in | demo@bigfm.dubai / DemoPass123! | User is authenticated and lands on Home; session persists on reload |  | Not Run
A-02 | Authentication | Login - wrong password | P1 | Both | Negative | On Login screen | 1. Enter valid email + wrong password 2. Submit | demo@bigfm.dubai / wrongpass | Friendly error shown; NOT logged in; no crash; no 'clear cache' prompt |  | Not Run
A-03 | Authentication | Onboarding gate | P1 | Both | Functional | New user with onboarding_complete=false | 1. Log in as a fresh user 2. Observe redirect | new signup | User is redirected to onboarding, not Home, until onboarding completes |  | Not Run
A-04 | Authentication | Logout | P2 | Both | Functional | Logged in | 1. Open profile/menu 2. Tap Logout | - | Session cleared; redirected to Login; protected routes no longer accessible |  | Not Run
HS-01 | Home / Shell | Home loads with shelves | P0 | Web | Smoke | Logged in | 1. Open Home (/) 2. Wait for load | - | Header, filter chips, and shelves render; no blank screen; no console errors |  | Not Run
HS-02 | Home / Shell | Sidebar chip counts | P1 | Web | Functional | Logged in | 1. Observe left sidebar / filter chips 2. Compare counts to content | - | Chips show live counts (Radio, Shop cats, News, Games); zero-count items hidden |  | Not Run
HS-03 | Home / Shell | Radio chip switches feed | P0 | Web | Functional | On Home, chip=All | 1. Click 'Radio' chip 2. Observe feed | - | Feed switches to a station grid (home-station-grid); visibly different from default feed |  | Not Run
HS-04 | Home / Shell | Empty-state doctrine | P1 | Both | Functional | A shelf/category has no content | 1. View Home default feed 2. Look for empty shelves | - | Shelves with no content are hidden entirely; no 'nothing yet' placeholder in default feed |  | Not Run
R&-01 | Radio & Playback | Play an AI channel | P0 | Both | Functional | Logged in | 1. Open a station tile in 'Your stations' 2. Tap play | any channel | Audio starts; persistent player bar shows station + now-playing segment |  | Not Run
R&-02 | Radio & Playback | Play imported world station | P0 | Both | Functional | On Radio browse / all stations | 1. Search/browse to a world station 2. Tap play | e.g. Classic FM UK | Stream plays; station detail shows tags/country/language |  | Not Run
R&-03 | Radio & Playback | Persistent player continue | P1 | Both | Functional | A station is playing | 1. Navigate to another tab/page 2. Observe player | - | Playback continues; player bar persists; Continue-listening shows the station |  | Not Run
R&-04 | Radio & Playback | Search stations | P1 | Both | Functional | On stations/search | 1. Type a query 2. Review results | 'jazz' | Relevant stations returned; each shows artwork (never blank) |  | Not Run
SA-01 | Station Artwork | Every station has art | P0 | Web | Functional | On Radio browse | 1. Open browse list 2. Inspect each station tile | - | Every tile shows an image: real logo, AI art, or genre-coloured initials placeholder — never blank |  | Not Run
SA-02 | Station Artwork | On-demand AI on first open | P1 | Web | Functional | Open a placeholder-only imported station | 1. Open station detail (/radio/station/imp_...) 2. Wait ~20-40s, refresh | a station with placeholder art | AI cover is generated from name/genre and appears on refresh; art_source becomes 'ai' |  | Not Run
SA-03 | Station Artwork | Owner artwork manager visible | P1 | Web | Functional | Logged in as admin OR station owner | 1. Open a station detail page 2. Look for owner tools | admin@bigfm.dubai / AdminPass123! | 'Station artwork · owner tools' panel shows Generate / Upload / Reset controls |  | Not Run
SA-04 | Station Artwork | Owner controls hidden for non-owner | P0 | Web | Negative | Logged in as a normal (non-owner) user | 1. Open the same station detail page | demo@bigfm.dubai / DemoPass123! | Owner artwork panel is NOT shown; generate/upload/clear API returns 403 if called |  | Not Run
SA-05 | Station Artwork | Owner generates AI art | P1 | Web | Functional | Logged in as admin/owner on station detail | 1. Click 'Generate AI artwork' 2. Wait for completion toast | - | New AI cover replaces placeholder; success toast; art persists on reload |  | Not Run
SA-06 | Station Artwork | Owner uploads logo | P1 | Web | Functional | Logged in as admin/owner | 1. Click 'Upload logo' 2. Choose a JPG/PNG/WebP < 5MB | sample logo | Uploaded image becomes the station art (art_source='owner'); >5MB or wrong type rejected with a clear error |  | Not Run
SA-07 | Station Artwork | Owner resets art | P2 | Web | Functional | Owner station has custom art | 1. Click 'Reset' | - | Art reverts to default/placeholder; can be regenerated again |  | Not Run
SA-08 | Station Artwork | Flagship shelf self-heal | P1 | Web | Functional | Flagship missing art (fresh deploy) | 1. Load Home 2. Wait ~18s and refresh | - | Flagship tiles without art auto-generate AI covers and appear; no blank flagship tiles |  | Not Run
C-01 | Clips | Clips shelf renders | P1 | Both | Functional | Logged in | 1. Scroll to 'Clips' shelf on Home | - | Vertical 9:16 clip cards render with artwork; shelf hidden if empty |  | Not Run
C-02 | Clips | Sponsored clip is first + badged | P0 | Both | Functional | Active advertiser campaign exists | 1. View Clips shelf | - | First clip shows a 'SPONSORED' badge + branded cover image (not a plain gradient) |  | Not Run
C-03 | Clips | Tap-to-Claim issues code | P0 | Web | Functional | Logged in; sponsored clip present | 1. Tap the sponsored clip 2. In the sheet, tap 'Claim this offer' | - | Claim sheet opens; on claim a redemption code (RL-XXXXXX) + success state shown |  | Not Run
C-04 | Clips | Claim is idempotent | P1 | Web | Functional | User already claimed this offer | 1. Tap sponsored clip again 2. Claim | same user + campaign | Same code returned; 'Already claimed' state; no duplicate credit |  | Not Run
C-05 | Clips | Station clip opens station | P2 | Both | Functional | Clips shelf has station clips | 1. Tap a non-sponsored clip | - | Navigates to the station / radio player |  | Not Run
S&-01 | Shop & Eat | Category chips filter venues | P0 | Web | Functional | On Home with venues | 1. Click 'Eat' chip 2. Then 'Salons', 'Fitness', 'Shops' | - | Venue shelf filters to only that category each time; counts match |  | Not Run
S&-02 | Shop & Eat | Sponsored venue marked | P0 | Web | Functional | A venue has an active promotion | 1. View venue shelf | - | First card of a promoted set shows a 'Sponsored' pill; ordering is sponsored-first |  | Not Run
S&-03 | Shop & Eat | Market-scoped venues | P1 | Both | Functional | User geo resolves to Dallas | 1. Open Home venue shelf | Dallas-IP user | Shows Dallas venues (Smoke & Oak BBQ, etc.); Dubai user sees Dubai venues; never empty |  | Not Run
S&-04 | Shop & Eat | Sell CTA at bottom | P2 | Web | Functional | On /shop | 1. Scroll to bottom of Shop page | - | 'Sell on RadioLife' / 'Merchant Dashboard' banner appears at the BOTTOM, not between categories and content |  | Not Run
S&-05 | Shop & Eat | Order-by-chat floating capsule | P2 | Web | Functional | On /shop | 1. Observe right side of screen 2. Tap the capsule | - | 'Order by chat' floating capsule pinned bottom-right; opens the AI concierge |  | Not Run
S&-06 | Shop & Eat | Quick-Buy sheet | P2 | Web | Functional | On a shopping sub-category | 1. Tap a product 2. Use Quick-Buy | - | Quick-Buy sheet opens; memberships/discounts applied; add to cart works |  | Not Run
B&-01 | BigPoints & Wallet | Currency shows BigPoints | P1 | Both | Regression | Anywhere currency is shown | 1. Check wallet, earn labels, offers | - | All currency reads 'BigPoints' — NO 'BigCoin' or 'BC' anywhere |  | Not Run
B&-02 | BigPoints & Wallet | Wallet balance | P1 | Both | Functional | Logged in | 1. Open Wallet | - | Balance + tier shown; matches points pill in header |  | Not Run
B&-03 | BigPoints & Wallet | Earn from action | P1 | Both | Functional | Logged in | 1. Complete an earn action (e.g. claim / play) 2. Check wallet | - | Balance increases by the expected amount; transaction logged |  | Not Run
OO-01 | On-Air Offers | Offer card while playing | P1 | Web | Functional | A station with an active offer is playing | 1. Play the station 2. Observe card above player | - | On-air offer card shows the relevant merchant offer synced to the station |  | Not Run
OO-02 | On-Air Offers | Claim from on-air card | P2 | Web | Functional | On-air offer card visible | 1. Tap the offer's claim CTA | - | Routes to the offer/claim; no dead-end |  | Not Run
G--01 | Games - Predict & Win | Predictions list loads | P1 | Web | Functional | Logged in | 1. Open Predict & Win (/predict-win) | - | Curated prediction markets load; categories filterable; no junk/unapproved questions |  | Not Run
G--02 | Games - Predict & Win | Make a pick | P1 | Web | Functional | On a prediction | 1. Select an option 2. Submit | - | Pick locked in; status shows 'Locked in'; reflected in My Picks |  | Not Run
G--03 | Games - Trivia | Trivia categories load | P1 | Web | Functional | Logged in | 1. Open Trivia (/trivia) | - | City-aware categories shown (e.g. DFW/your city); header shows resolved market |  | Not Run
G-01 | Games | Spin & Win / Play hub | P2 | Both | Functional | Logged in | 1. Open Play/Games | - | Live games listed; can start a game; earns BigPoints |  | Not Run
N-01 | News | City-aware headlines | P1 | Both | Functional | Geo resolved | 1. Open Home news shelf / News tab | Dallas-IP user | Headlines request passes the detected market; feed reflects the city where possible |  | Not Run
N-02 | News | Breaking banner | P2 | Both | Functional | A breaking item exists | 1. Observe top of Home / News | - | Breaking banner shown; tapping opens the story/News |  | Not Run
A-05 | Ads | Leaderboard + in-feed banners | P1 | Web | Functional | Non-premium user | 1. Load Home 2. Observe ad slots | - | Banner slots render from active campaigns; premium users see fewer/no ads |  | Not Run
A-06 | Ads | Impression/click tracking | P2 | Web | Functional | Sponsored station/clip shown | 1. View then click a sponsored item | - | Impression fired on view; click fired on tap (verify via network/logs) |  | Not Run
DT-01 | Design / Theme | Dark/light toggle | P1 | Web | Functional | Logged in | 1. Toggle theme (theme-toggle) 2. Navigate key pages | - | Theme flips app-wide; persists; no washed-out or unreadable elements |  | Not Run
DT-02 | Design / Theme | Predict & Win light theme | P0 | Web | Functional | Theme = light | 1. Open /predict-win | - | Background/text/cards/chips all legible in light; no black-on-black or white-on-white |  | Not Run
DT-03 | Design / Theme | Trivia light theme | P1 | Web | Functional | Theme = light | 1. Open /trivia | - | Category cards + sidebar legible in light and dark |  | Not Run
L-01 | Location | Single geo source | P1 | Both | Functional | Fresh session | 1. Load app 2. Check header city, news, venues, trivia city | - | All reflect ONE detected city; no hardcoded Orlando/NY/Dubai mismatch |  | Not Run
MA-01 | Mobile App | Home dark YouTube shell | P0 | Mobile | Smoke | Logged in on Expo app | 1. Open Home tab | - | Dark themed Home; header with menu + points; sticky filter chips; no blank screen |  | Not Run
MA-02 | Mobile App | Swipeable shelves w/ peek | P1 | Mobile | Functional | On mobile Home | 1. Swipe each shelf horizontally | - | Shelves scroll horizontally; next card peeks (half-card); smooth 60fps |  | Not Run
MA-03 | Mobile App | Slide-out drawer | P1 | Mobile | Functional | On mobile Home | 1. Tap the menu (hamburger) 2. Tap a drawer item | - | Drawer slides in with Primary + Discover nav; item navigates and drawer closes |  | Not Run
MA-04 | Mobile App | Bottom tab bar | P1 | Mobile | Functional | On any tab | 1. Tap between tabs | - | Dark tab bar; selected tab clearly differs in colour from unselected; correct screen loads |  | Not Run
MA-05 | Mobile App | Sponsored clip claim (mobile) | P1 | Mobile | Functional | Sponsored clip on mobile Home | 1. Tap the sponsored clip | - | Claim fires; an inline banner shows the redemption code; dismissable |  | Not Run
MA-06 | Mobile App | Pull to refresh | P2 | Mobile | Functional | On mobile Home | 1. Pull down to refresh | - | Feed reloads; spinner uses brand colour |  | Not Run
MA-07 | Mobile App | Safe areas | P2 | Mobile | Functional | Device with notch | 1. Observe header + tab bar | - | Content respects safe areas; nothing clipped by notch/home indicator |  | Not Run
M-01 | Merchant | Merchant dashboard access | P1 | Web | Functional | Logged in as merchant | 1. Open Merchant Dashboard | test@bigfm.dubai / TestUser123! | Dashboard loads; can manage menu/products/promotions/memberships |  | Not Run
M-02 | Merchant | Create a promotion | P2 | Web | Functional | Merchant with a business | 1. Create/boost a promotion | - | Business becomes sponsored; appears sponsored-first on the venue shelf |  | Not Run
A-07 | Admin | Admin login + panel | P1 | Web | Functional | Admin account | 1. Log in as admin 2. Open admin routes | admin@bigfm.dubai / AdminPass123! | Admin panel accessible; non-admins are blocked from admin routes |  | Not Run
A-08 | Admin | Approvals / sponsorships | P2 | Web | Functional | Pending items exist | 1. Review approvals / trivia & station sponsorships | - | Admin can approve/reject; changes reflect in consumer app |  | Not Run
C-06 | Cross-platform | Same data web vs mobile | P1 | Both | Functional | Same user on both | 1. Compare Home shelves on web and mobile | demo@bigfm.dubai | Stations, clips, venues, points match (served by one /api); no platform-only divergence |  | Not Run
N-03 | Non-functional | Home load performance | P2 | Both | Performance | Normal network | 1. Cold load Home 2. Measure time to interactive | - | Home usable within a few seconds; skeletons/loaders shown while fetching |  | Not Run
N-04 | Non-functional | Graceful API failure | P1 | Both | Negative | Simulate a failed endpoint | 1. Block one shelf's API 2. Load Home | - | That shelf is hidden or shows a friendly error+retry; rest of Home still works; no crash |  | Not Run
N-05 | Non-functional | Broken image fallback | P2 | Both | Negative | A station has a dead image URL | 1. Open that station | - | Falls back to placeholder/initials; layout not broken |  | Not Run
N-06 | Non-functional | Deep link / refresh | P2 | Web | Functional | On a deep page | 1. Refresh the browser on /shop, /trivia, /predict-win | - | Page reloads correctly (no 404); auth preserved |  | Not Run

## Summary
RadioLife UAT — Summary
Overall status
Total test cases | By Priority
Pass | P0
Fail | P1
Blocked | P2
N/A
Not Run | By Module (total / pass)
% Pass | Authentication
Home / Shell
Radio & Playback
Station Artwork
Clips
Shop & Eat
BigPoints & Wallet
On-Air Offers
Games - Predict & Win
Games - Trivia
Games
News
Ads
Design / Theme
Location
Mobile App
Merchant
Admin
Cross-platform
Non-functional